## Action Items (hidden)
Action Items : |  |  |  |  | Low |  | Medium |  | High
Sr. No. | Scenario | Action items | Impact | Status | Severity | Reported On | Expected date to be closed | Actually Closed On | Remarks
1 | All
2
3
4
5
6
7
8
9
10
11
12

## Project Summary
Overall Status
Activities | Planned Start date | Planned End Date | Actual Start Date | Actual End Date | Current Status | % Completion | Remarks
Discovery | 2025-05-14 | 2025-05-16 | 2025-05-14 | 2025-05-16 | Completed | 100%
Setup | 2025-06-19 | 2025-06-22 | 2025-05-15 | 2025-06-10 | Completed | 100%
Scripting | 2025-05-20 | 2025-06-03 | 2025-05-26 | 2025-06-10 | Completed | 100%
Execution | 2025-06-04 | 2025-06-13 | 2025-06-09 |  | In Progress | 0%
'

## Detailed Project _Plan
Overall Project Status :
Application | Activities | Planned Start date | Planned End Date | Actual Start Date | Actual End Date | Current Status | Completion Status | Week 0 | [6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Responsibility | Remarks
 | time axis 2025-05-12 to 2025-07-06
SAL - TIES | Discovery | 2025-05-14 | 2025-05-16 | 2025-05-14 | 2025-05-16 |  |  | 2025-05-17: Weekend; 2025-05-24: Weekend; 2025-05-31: Weekend; 2025-06-07: Weekend; 2025-06-14: Weekend; 2025-06-21: Weekend; 2025-06-28: Weekend; 2025-07-05: Weekend
| Availability of functionally stable production equivalent test environment | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | Completed | 100% | [56 empty] | Client | bar: 2025-05-14
| Environment accessibility of Testing environment | 2025-05-14 | 2025-05-16 | 2025-05-15 | 2025-05-16 | Completed | [57 empty] | Client | bar: 2025-05-15 to 2025-05-16
| Application Walkthrough for SAL | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | Completed | [57 empty] | Client, QK | bar: 2025-05-14
| Application Walkthrough for TIES | 2025-05-15 | 2025-05-16 | 2025-05-15 | 2025-05-16 | Completed | [57 empty] | Client, QK | bar: 2025-05-15 to 2025-05-16
| Setup | 2025-06-19 | 2025-06-22 | 2025-05-15 | bar: 2025-05-12 to 2025-05-16; 2025-05-19 to 2025-05-23; 2025-05-26 to 2025-05-30; 2025-06-02 to 2025-06-06; 2025-06-09 to 2025-06-13; 2025-06-16 to 2025-06-20; 2025-06-23 to 2025-06-27; 2025-06-30 to 2025-07-04
| Resource Onboarding | 2025-05-15 | 2025-05-19 | 2025-05-15 | 2025-05-19 | Completed | 100% | [56 empty] | Client | bar: 2025-05-15 to 2025-05-16; 2025-05-19
| Software Installation | 2025-05-19 | 2025-06-20 | 2025-05-22 | 2025-05-20 | Completed | bar: 2025-05-22
| AppDynamics Setup | 2025-05-19 | 2025-06-04 | 2025-06-06 | 2025-06-10 | Completed | [57 empty] | Client, QK | bar: 2025-06-06; 2025-06-10
| Load-Generator Access | 2025-05-19 | 2025-06-21 | 2025-05-19 | 2025-05-22 | Completed | [57 empty] | Client, QK | bar: 2025-05-19 to 2025-05-22
| Scripting | 2025-05-20 | 2025-06-20 | 2025-05-19 | 2025-06-06 | bar: 2025-05-12 to 2025-05-16; 2025-05-19 to 2025-05-23; 2025-05-26 to 2025-05-30; 2025-06-02 to 2025-06-06; 2025-06-09 to 2025-06-13; 2025-06-16 to 2025-06-20; 2025-06-23 to 2025-06-27; 2025-06-30 to 2025-07-04
| Workload profile Sharing and confirmation from Client Team | 2025-05-19 | 2025-05-21 | 2025-05-19 | 2025-06-06 | Completed | 100% | [56 empty] | Client | bar: 2025-05-27 to 2025-05-30; 2025-06-02 to 2025-06-06
| Sharing of Transactional data (scripting purpose). | 2025-05-20 | 2025-06-03 | 2025-05-20 | 2025-06-10 | Completed | [57 empty] | Client | bar: 2025-05-22 to 2025-05-23; 2025-05-26 to 2025-05-30; 2025-06-02 to 2025-06-06; 2025-06-09 to 2025-06-11
| Scripting of Identified scenario | 2025-05-21 | 2025-06-03 | 2025-05-21 | 2025-06-06 | Completed | [57 empty] | Client, QK | bar: 2025-05-22 to 2025-05-23; 2025-05-26 to 2025-05-30; 2025-06-02 to 2025-06-06
| Execution | 2025-06-09 | 2025-07-04 | 2025-06-09 | bar: 2025-05-12 to 2025-05-16; 2025-05-19 to 2025-05-23; 2025-05-26 to 2025-05-30; 2025-06-02 to 2025-06-06; 2025-06-09 to 2025-06-13; 2025-06-16 to 2025-06-20; 2025-06-23 to 2025-06-27; 2025-06-30 to 2025-07-04
| Smoke test execution with each scenario | 2025-06-09 | 2025-06-10 | 2025-06-09 |  | In Progress | 0% | [56 empty] | Client, QK | bar: 2025-06-09 to 2025-06-13; 2025-06-16 to 2025-06-20; 2025-06-23
| Test Data creation and Script updation | 2025-06-10 | 2025-06-20 | 2025-06-10 |  | In Progress | bar: 2025-06-10 to 2025-06-13; 2025-06-16 to 2025-06-19; 2025-06-23
| Load Test with 10% user-load | 2025-06-18 | 2025-06-24 | 2025-06-18 |  | In Progress | bar: 2025-06-18 to 2025-06-19
| Load Test with 50% user-load | 2025-06-25 | 2025-06-25 |  |  | Not Started
| Load Test with 80% user-load | 2025-06-26 | 2025-06-27 |  |  | Not Started
| Load Test with 100% user-load | 2025-06-30 | 2025-07-01 |  |  | Not Started
| Soak Test with 80 user-load | 2025-07-02 | 2025-07-03 |  |  | Not Started
| Root cause Analysis and Report Sharing | 2025-06-23 | 2025-07-03 |  |  | Not Started
| Project closure | 2025-07-04 | 2025-07-04 |  |  | Not Started

## Daily Status Tracker
Week | Date | Activities | Status | Downtime in Hr | Remarks
Week -1 | 2025-05-19 | Resource Onboarding | In Progress
|  | Confirmation of Navigational Flow | In Progress
|  | Access to Load Generator | In Progress
| 2025-05-21 | Resource Onboarding | Completed
|  | Confirmation of Navigational Flow | Completed
|  | Access to Load Generator | In Progress
|  | KT on the additional Flow | Completed
|  | Kick-Off Presentation | Completed
| 2025-05-22 | Access to Load Generator | Completed
|  | Installation of Load-Runner | Completed
| 2025-05-23 | Scripting started for TIES scenario | In Progress
|  | Installation of Load-Runnerin both Load Injecter | Completed
Week - 2 | 2025-05-26 | Discussion on the SAL navigation for "Transporter Fee" | Completed
|  | Discussion on the SAL navigation for "Dealer Master" | In Progress
|  | Scripting on "Transporter Fee" | In Progress
|  | Scripting on TIES scenarios | In Progress
| 2025-05-27 | Requested Workload Model | In Progress
|  | Discussion on the SAL navigation for "Dealer Master" | Completed
|  | Scripting on "Transporter Fee" | In Progress
|  | Scripting on TIES scenarios | In Progress
| 2025-05-28 | Discussion on the SAL navigation for "D22" and "Process Track" | Completed
|  | Scripting on "Transporter Fee" | Completed
|  | Scripting on TIES scenarios | Completed
|  | Scripting on "D22" | In Progress
| 2025-05-29 | Scripting on "D22" | In Progress |  | Got a access of two pages which requested, Understanding is pending
|  | Scripting on "Dealer Sales" | In Progress |  | Divide into the 4 part, 3 parts recording is done
|  | Scripting on "Process Track" | In Progress
| 2025-05-30 | Scripting on "D22" | In Progress
|  | Scripting on "Dealer Sales" | In Progress |  | Recording done
|  | Scripting on "Process Track" | In Progress
|  | Scripting on "RSY" | In Progress |  | Recording done
| 2025-05-31 | Scripting on "D22" | Completed
|  | Scripting on "Dealer Sales" | In Progress
|  | Scripting on "Process Track" | In Progress |  | Only one Transaction is pending due to facing the issue so need to discuss with TKM Team
|  | Scripting on "RSY" | In Progress
Week - 3 | 2025-06-02 | Scripting on "Dealer Sales" | In Progress
|  | Scripting on "Process Track" | In Progress
|  | Scripting on "RSY" | In Progress
| 2025-06-03 | Scripting on "Dealer Sales" | In Progress
|  | Scripting on "Process Track" | In Progress
|  | Scripting on "RSY" | In Progress
| 2025-06-04 | Scripting on "Dealer Sales" | In Progress |  | facing data issue
|  | Scripting on "Process Track" | In Progress |  | Awaiting the confirmation for the descoping of a page
|  | Scripting on "RSY" | In Progress
|  | Scripting on "Alliance" | In Progress
|  | Scripting on "Export" | Awaiting |  | Require assistance of TKM for scripting
| 2025-06-04 | Scripting on "Dealer Sales" | Completed
|  | Scripting on "Process Track" | Completed
|  | Scripting on "RSY" | Completed |  | VIN numbers and suffix associated with the VIN needs to be unlocked
|  | Scripting on "Alliance" | In Progress
|  | Scripting on "Export" | In Progress
|  | Stock need to be added for RSY | Completed
|  | SO Interface Job to be automated | In Progress
|  | Test Data for PT Execution | In Progress
|  | Workload model for Transporter Fee and Process Track | In Progress
| 2025-06-05 | Scripting on "Alliance" | Completed
|  | Scripting on "Export" | Completed
|  | Workload model for Transporter Fee and Process Track | Completed
|  | AppDynamics Installation | In Progress
|  | Test Data for PT Execution | In Progress
|  | SO Interface Job to be automated | In Progress
Week - 4 | 2025-06-09 | Additional Scripting on "Alliance" | In Progress
|  | AppDynamics Installation | In Progress
|  | Test Data for PT Execution | In Progress
|  | SO Interface Job to be automated | Completed
| 2025-06-10 | Additional Scripting on "Alliance" | Completed
|  | AppDynamics Installation | Completed
|  | Test Data for PT Execution | In Progress
| 2025-06-10 | Sanity Run | In Progress
|  | Availability of Laptop | Completed
|  | Laptop access to LG | In Progress
|  | Fixing of SAL Scenarios for Sanity Run | In Progress
Week - 5 | 2025-06-18 | Test Data shared for some scenarios | In Progress
|  | Updation of some script based on added test-data | In Progress
| 2025-06-19 | Discussed the Load Model with the client | In Progress
|  | Discussed the Test data requirement with the client | In Progress
|  | Test Script validation in progress with different test data | In Progress
| 2025-06-20 | SAL Baseline Test conducted | In Progress
|  | Discussion on Manual Upload scenario | In Progress
|  | Production DB AWR reports requested | In Progress
Week - 6 | 2025-06-20 | SAL Baseline Test conducted | In Progress
|  | Discussion on Manual Upload scenario | In Progress
|  | Production DB AWR reports requested | In Progress

## Scripting_Status
Scripting summary :
S.No. | Module |  | Total Scripts | To Be initiated | In Progress | Completed | Application wise script completion | On Hold Scenarios | Script Validation% | Remarks
1 | SAL |  | 18 | 0 | 0 | 18
2 | TIES |  | 5 | 0 | 0 | 5
| Total |  | 23 | 0 | 0 | 23 | 0 | 0 | 0
| Module | Script | Status
| SAL | Delear Sales (Without Stock) | Completed
|  | Rsy (With Stock) | Completed
|  | Alliance | Completed
|  | Export | Completed
|  | Process Track | Completed
|  | D22 | Completed
| TIES | OPPD_Packing_plan | Completed
|  | IMPEX | Completed
|  | ILCD_Validation | Completed
|  | ILCD_Vanning_Validation | Completed
|  | INVOICE_EXPORT&COMMERCIAL | Completed

## Open Points
S.No. | Open Item list | Status | Open date | Closed Date | Ageing in days | Responsibility | Remarks
1 | Logn Credentials for SAL | Closed | 2025-05-16 | 2025-05-21 | 5 | Client team
2 | Access to Load Generator Machine | Closed | 2025-05-19 | 2025-05-21 | 2 | Client team
3 | Navigational Flow Confirmation | Closed | 2025-04-19 | 2025-05-21 | 2 | Client team
4 | Access to application from LG | Closed | 2025-05-21 | 2025-05-22 | 1 | Client Team
5 | Master Test Data requested for SAL | Closed | 2025-05-23 | 2025-05-26 | 3 | Client Team
6 | Workload Model for Sal-TIES | Closed | 2025-05-27 | 2025-06-06 | 10 | Client Team
7 | Need Assistance for "Export" scenario | Closed | 2025-06-04 | 2025-06-05 | 1 | Client Team
8 | Confirmation on Dedscoping of a page in "Process Tack" | Closed | 2025-06-02 | 2025-06-05 | 3 | Client Team
9 | Stock need to be added for RSY | Closed | 2025-06-05 | 2025-06-05 | 0 | Client Team
10 | RSY - SO Interface Job to be automated | Closed | 2025-06-05 | 2025-06-09 | 4 | Client Team
11 | RSY - VIN numbers and suffix associated with the VIN needs to be unlocked | Closed | 2025-06-05 | 2025-06-06 | 1 | Client Team
12 | Test Data for PT Run | Closed | 2025-06-09 | 2025-06-10 | 1 | Client Team
13 | RSY Test Data giving "Stock Not Found" | Closed | 2025-06-10 | 2025-06-11 | 1 | Client Team
14 | Alliance Test Data - VIN Numbers not updated | Closed | 2025-06-10 | 2025-06-11 | 1 | Client Team
15 | Process Track - Need Test Data for Dispatch Car Parking | Closed | 2025-06-10 | 2025-06-11 | 1 | Client Team
16 | Access of LG machine from Akheem's Laptop | Closed | 2025-06-12 | 2025-06-13 | 1 | Client Team
17 | Test Data (Dealer sales) - Test Data should not include Plant 2 data | Closed | 2025-06-12 | 2025-06-16 | 1 | Client Team
18 | Test Data (Process Track) - VIN Numbers required | Closed | 2025-06-12 | 2025-06-16 | 1 | Client Team
19 | Test Data (Vehicle Manitenance) - Need data for Aged Vehicle Maintenance | Closed | 2025-06-12 | 2025-06-16 | 1 | Client Team
20 | Manual Entry Confirmation navigates to an incorrect screen | Closed | 2025-06-16 | 2025-06-17 | 1 | Client Team
21 | Test Data for the scenarios | Closed | 2025-06-18 | 2025-06-18 | 1 | Client Team
22 | RSY Test Data Error - "Stock Not found for selected error" | Closed | 2025-06-18 | 2025-06-18 | 1 | Client Team
23 | Alliance Test Data error - Bay Not Found | Closed | 2025-06-18 | 2025-06-18 | 1 | Client Team
24 | D22 Test Data Error - Stop Pop-up | Closed | 2025-06-18 | 2025-06-18 | 1 | Client Team
25 | Mass Test Data for SAL scenarios | Open | 2025-06-19 |  | New | Client Team
26 | Restore point creation after mass test data is created | Open | 2025-06-19 |  | New | Client Team
27 | TPH for "RSY Stock Transfer" and "Alliance- RSY Stock Transfer" to be confirmed | Open | 2025-06-19 |  | New | Client Team
28 | Exports GRN - LOT confirmation page is not displaying the newly created LOT | Closed | 2025-06-19 | 2025-06-20 | 1 | Client Team
29 | AWR Reports from Production DB | Open | 2025-06-19 |  | New | Client Team

## Runs Tracker
Sr # | Date | Run Id | Module/ Scenarios | No of Users | Load test Duration | Achieved txns / hour | No of pages @90Percentile > 5 sec | Pass % | Run Status Pass/Fail

## Run Tracker (hidden)
Sr # | Date | Run Id | Module/ Scenarios | Scenarios Included | No of Users | Load test Duration | Ramp up | Pre-Test Changes | Achieved txns / hour | Think Time | Pacing | No of pages @90 Percentile > 5 sec | Pass % | CPU Utilization | Mem Utilization | Observations/RCA | RCCA/ Tuning Recommendation | % Improvement in Application Performance | Run Status Pass/Fail | SLA Status
[20 empty] | 90th Percentile RT < 5 sec | Pass % = 100% | CPU & Mem utilisation < 60%
[19 empty] | Pass/Fail | Met/Not Met | Met/Not Met | Met/Not Met

## Defect Tracker (hidden)
Run ID | Defect ID | Defect Description | Start Date | End Date | Ageing | Status | Remarks