## Action Items (hidden)
Action Items : |  |  |  |  | Low |  | Medium |  | High
Sr. No. | Scenario | Action items | Impact | Status | Severity | Reported On | Expected date to be closed | Actually Closed On | Remarks
1 | All
2
3
4
5
6
7
8
9
10
11
12

## Project Summary
Overall Status
Activities | Planned Start date | Planned End Date | Actual Start Date | Actual End Date | Current Status | % Completion | Remarks
Discovery | 2025-05-14 | 2025-05-16 | 2025-05-14 | 2025-05-16 | Completed | 100%
Setup | 2025-06-19 | 2025-06-22 | 2025-05-15 |  | In Progress | 75%
Scripting | 2025-05-20 | 2025-06-03 | 2025-05-26 |  | In Progress | 0%
Execution | 2025-06-04 | 2025-06-13 |  |  |  | 0%
'

## Detailed Project _Plan
Overall Project Status :
Application | Activities | Planned Start date | Planned End Date | Actual Start Date | Actual End Date | Current Status | Completion Status | Week 0 | [6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Responsibility | Remarks
 | time axis 2025-05-12 to 2025-06-22
SAL - TIES | Discovery | 2025-05-14 | 2025-05-16 | 2025-05-14 | 2025-05-16 |  |  | 2025-05-17: Weekend; 2025-05-24: Weekend; 2025-05-31: Weekend; 2025-06-07: Weekend; 2025-06-14: Weekend; 2025-06-21: Weekend
| Availability of functionally stable production equivalent test environment | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | Completed | 100% | [42 empty] | Client | bar: 2025-05-14
| Environment accessibility of Testing environment | 2025-05-14 | 2025-05-16 | 2025-05-15 | 2025-05-16 | Completed | [43 empty] | Client | SAL - pending | bar: 2025-05-15 to 2025-05-16
| Application Walkthrough for SAL | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | Completed | [43 empty] | Client, QK | bar: 2025-05-14
| Application Walkthrough for TIES | 2025-05-15 | 2025-05-16 | 2025-05-15 | 2025-05-16 | Completed | [43 empty] | Client, QK | bar: 2025-05-15 to 2025-05-16
| Setup | 2025-06-19 | 2025-06-22 | 2025-05-15 | bar: 2025-05-12 to 2025-05-16; 2025-05-19 to 2025-05-23; 2025-05-26 to 2025-05-30; 2025-06-02 to 2025-06-06; 2025-06-09 to 2025-06-13; 2025-06-16 to 2025-06-20
| Resource Onboarding | 2025-05-15 | 2025-05-19 | 2025-05-15 | 2025-05-19 | Completed | 75% | [42 empty] | Client | bar: 2025-05-15 to 2025-05-16; 2025-05-19
| Software Installation | 2025-05-19 | 2025-06-20 | 2025-05-22 | 2025-05-20 | Completed | bar: 2025-05-22
| AppDynamics Setup | 2025-05-19 | 2025-06-04 |  |  | Not Started | [43 empty] | Client, QK
| Load-Generator Access | 2025-05-19 | 2025-06-21 | 2025-05-19 | 2025-05-22 | Completed | [43 empty] | Client, QK | bar: 2025-05-19 to 2025-05-22
| Scripting | 2025-05-20 | 2025-06-03 | bar: 2025-05-12 to 2025-05-16; 2025-05-19 to 2025-05-23; 2025-05-26 to 2025-05-30; 2025-06-02 to 2025-06-06; 2025-06-09 to 2025-06-13; 2025-06-16 to 2025-06-20
| Workload profile Sharing and confirmation from Client Team | 2025-05-19 | 2025-05-21 |  |  | Not Started | 0% | [42 empty] | Client | bar: 2025-05-27
| Sharing of Transactional data (scripting purpose). | 2025-05-20 | 2025-06-03 |  |  | In Progress | bar: 2025-05-22 to 2025-05-23; 2025-05-26 to 2025-05-27
| Scripting of Identified scenario | 2025-05-21 | 2025-06-03 |  |  | In Progress | [43 empty] | Client, QK | bar: 2025-05-22 to 2025-05-23; 2025-05-26 to 2025-05-27
| Execution | 2025-06-04 | 2025-06-13 | bar: 2025-05-12 to 2025-05-16; 2025-05-19 to 2025-05-23; 2025-05-26 to 2025-05-30; 2025-06-02 to 2025-06-06; 2025-06-09 to 2025-06-13; 2025-06-16 to 2025-06-20
| Smoke test execution with each scenario | 2025-06-04 | 2025-06-04 |  |  | Not Started | 0% | [42 empty] | Client, QK
| Load Test with 10% user-load | 2025-06-05 | 2025-06-06 |  |  | Not Started
| Load Test with 50% user-load | 2025-06-09 | 2025-06-10 |  |  | Not Started
| Load Test with 80% user-load | 2025-06-11 | 2025-06-12 |  |  | Not Started
| Load Test with 100% user-load | 2025-06-13 | 2025-06-16 |  |  | Not Started
| Soak Test with 80 user-load | 2025-06-17 | 2025-06-18 |  |  | Not Started
| Root cause Analysis and Report Sharing | 2025-06-05 | 2025-06-18 |  |  | Not Started
| Project closure | 2025-06-19 | 2025-06-20 |  |  | Not Started

## Daily Status Tracker
Week | Date | Activities | Status | Downtime in Hr | Remarks
Week -1 | 2025-05-19 | Resource Onboarding | In Progress
|  | Confirmation of Navigational Flow | In Progress
|  | Access to Load Generator | In Progress
| 2025-05-21 | Resource Onboarding | Completed
|  | Confirmation of Navigational Flow | Completed
|  | Access to Load Generator | In Progress
|  | KT on the additional Flow | Completed
|  | Kick-Off Presentation | Completed
| 2025-05-22 | Access to Load Generator | Completed
|  | Installation of Load-Runner | Completed
| 2025-05-23 | Scripting started for TIES scenario | In Progress
|  | Installation of Load-Runnerin both Load Injecter | Completed
Week - 2 | 2025-05-26 | Discussion on the SAL navigation for "Transporter Fee" | Completed
|  | Discussion on the SAL navigation for "Dealer Master" | In Progress
|  | Scripting on "Transporter Fee" | In Progress
|  | Scripting on TIES scenarios | In Progress
| 2025-05-27 | Requested Workload Model | In Progress
|  | Discussion on the SAL navigation for "Dealer Master" | In Progress
|  | Scripting on "Transporter Fee" | In Progress
|  | Scripting on TIES scenarios | In Progress

## Application Functional readines
Mobile API Readiness
Application |  | Total Scenarios | working scenarios/ Code freezed* | Not working scenarios/Code not freezed yet* | % Application functional readiness
SAL |  | 7
Total |  | 7
Web Appllication Readiness :
Application |  | Total scenarios | working scenarios/ Code freezed* | Not working scenarios/Code not freezed yet* | % Application functional readiness | Remarks
TIES |  | 5
Total |  | 5
Issue Tracker :
Sr. No. | Scenario | Issue Description | Resolution | Status | Issue Raised On | Issue resolved On | Remarks
1
Delay Tracker:
Sr. No. | Delayed activity | Planned End Date | Actual End Date | Delayed by days | Current Status | Remarks
1

## Scripting_Status
Scripting summary :
S.No. | Module | Total Scripts | To Be initiated | In Progress | Completed | Application wise script completion | On Hold Scenarios | Script Validation% | Remarks
1 | SAL | 7 | 6 | 1
2 | TIES | 5 | 0 | 5
| Total | 12 | 6 | 6 | 0 | 0 | 0 | 0

## Open Points
S.No. | Open Item list | Status | Open date | Closed Date | Ageing in days | Responsibility | Remarks
1 | Logn Credentials for SAL | Closed | 2025-05-16 | 2025-05-21 | 5 | Client team
2 | Access to Load Generator Machine | Closed | 2025-05-19 | 2025-05-21 | 2 | Client team
3 | Navigational Flow Confirmation | Closed | 2025-04-19 | 2025-05-21 | 2 | Client team
4 | Access to application from LG | Closed | 2025-05-21 | 2025-05-22 | 1 | Client Team
5 | Master Test Data requested for SAL | Closed | 2025-05-23 | 2025-05-26 | 3 | Client Team
6 | Workload Model for Sal-TIES | Open | 2025-05-27 |  | New | Client Team

## Runs Tracker
Sr # | Date | Run Id | Module/ Scenarios | No of Users | Load test Duration | Achieved txns / hour | No of pages @90Percentile > 5 sec | Pass % | Run Status Pass/Fail

## Run Tracker (hidden)
Sr # | Date | Run Id | Module/ Scenarios | Scenarios Included | No of Users | Load test Duration | Ramp up | Pre-Test Changes | Achieved txns / hour | Think Time | Pacing | No of pages @90 Percentile > 5 sec | Pass % | CPU Utilization | Mem Utilization | Observations/RCA | RCCA/ Tuning Recommendation | % Improvement in Application Performance | Run Status Pass/Fail | SLA Status
[20 empty] | 90th Percentile RT < 5 sec | Pass % = 100% | CPU & Mem utilisation < 60%
[19 empty] | Pass/Fail | Met/Not Met | Met/Not Met | Met/Not Met

## Defect Tracker (hidden)
Run ID | Defect ID | Defect Description | Start Date | End Date | Ageing | Status | Remarks